## 2021 Roadmap
Priority | Project | Description | Launch Month | T-shirt size | Status | PRD Link | Design Link | 2021-02-01 | 2021-02-08 | 2021-02-15 | 2021-02-22 | 2021-03-01 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-04-05
P0 | Project Apollo | 2FA support for log in | March | S | Building |  |  | 2021-02-01: Eng; 2021-02-08: Eng; 2021-02-15: Eng; 2021-02-22: QA; 2021-03-01: Launch
P0 | Fig Discovery | Increase discovery of figs across the platform | April | L | Designing |  |  | Design | Design | Handoff | Eng | Eng | Eng | QA | Launch
P1 | Onboarding funnel | Increase top of funnel awareness | August | M | Planning & Scoping |  |  | Product | Product | Checkpoint | Design | Design | Checkpoint | Design | Handoff | Eng | Eng
P1 | Aries Surfaces | Use a DS model to strategically place Aries across more surfaces | August | M | Planning & Scoping |  |  | Product | Product | Product | Checkpoint | Design | Design | Design | Checkpoint | Design | Handoff
P1 | Desktop parity | Ensure feature parity with mobile | September | S | Blocked |  |  | 2021-02-08: Checkpoint; 2021-02-15: Design; 2021-02-22: Design; 2021-03-01: Handoff; 2021-03-08: Eng
P2 | Checkout flow | Support for express checkout and log in | May | XS | Not started
P2 | Sprout and grow | Planting more seeds and building a user flow | November | S | Not started
Cutline
P2 | Size support | Allow customers to add multiple sizes of items. |  | S | Not started
P2 | Entry point awareness | Audit of existing entry points |  | XL | Not started
Completed
P0 | Crowded house | Enable data exporting of customer base | January | XS | Live Experiment |  |  | 2021-02-01: Launch
P0 | Surf customizations | Allow customers to set their own filters and search preferences | January | M | Launched |  |  | 2021-02-01: QA; 2021-02-08: Launch

## Design Planning
UX ACTIVITY
Activity | Tasks | My Priority | Status | 2021-02-01 | 2021-02-08 | 2021-02-15 | 2021-02-22 | 2021-03-01 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-04-05
Thinking | Lean UX Grid - will circulate today | 1 | In progress | Thinking | Thinking | Design | Design | Design
| User story mapping | 2 | In progress |  |  |  | Prototype | Prototype | Validation | Thinking | Design
| Heuristics - Product Assesment | 3 | Not started |  |  |  |  | Testing | Handoff | Thinking | Prototype | Prototype | Testing
Design | User Flow | 3 | In progress
| Lo-def key wireframe | 4 | Not started
| Prototype | 6 | Not started
| Visual Ideations | 7 | Not started
| Test - users / stakeholders | 6 | Not started
Prototype & Test | Key UI Mock ups - Visual Defs | 8 | Not started
| Interactions | 9 | Not started
| UI Animations | 10 | Not started
| User test and validation | 9 | Not started